# Tab 2

# 🔥NRB 2026 - Six Pillars Strategic Framework

Event Owner: Jason Rosoff
 Event Dates: February 17-20, 2026 | Nashville, TN
 Investment: $400,000
 Last Updated: December 18, 2025

## 📋 Table of Contents

- Mission Clarity

- Thematic Foundation

- Audience Architecture

- Experience Design

- Operational Excellence

- Team Function Accountability

- Quick Reference & Action Items

## PILLAR 1: MISSION CLARITY

### 🎯 Primary Business Goal

Position PRAY.COM as the undisputed innovation leader in AI-powered ministry technology while converting NRB attendees into high-value pipeline opportunities that drive $2.28M in closed revenue.

### 📊 Success Metrics

| Metric | Target | Measurement Timeline |
| --- | --- | --- |
| Captured Contacts (MQLs) | 655 | Event Days 1-4 |
| Meetings Conducted | 193 (+27% vs 2025) | Event Days 1-4 |
| Deals Created | 66 (+21% vs 2025) | 30 Days Post-Event |
| Pipeline Value | $10.42M (+21% vs 2025) | 30 Days Post-Event |
| Deals Won | 19 (+21% vs 2025) | 90 Days Post-Event |
| Revenue Target | $2.28M | 90 Days Post-Event |
| Cost per Deal | $23,573 | 90 Days Post-Event |
| 90-Day ROI | 406% | 90 Days Post-Event |

Conversion Funnel:
 6,500 attendees → 655 contacts → 193 meetings → 66 deals → 19 wins → $2.28M

### 🎪 Secondary Metrics

- Speaking session attendance: 300+ attendees (Feb 20, 9:00-9:45 AM, Delta B Ballroom)

- America Prays 250 partnership commitments: 25 ministries

- Booth reputation: Maintain "Best in Show" status

- VIP interview completion: 100% of 29 pre-scheduled meetings

- Post-event engagement: Email opens >25%, demo scheduling >40%

### 🚫 Non-Negotiables

- Meeting Target: Achieve all 193 meetings across 4-day event

- Positioning Clarity: Complete PB-34554 & PB-34553 before campaign launch

- Demo Quality: Every booth interaction reinforces "loved, capable, needed" positioning

- Data Integrity: 100% of contacts captured in HubSpot with proper attribution

- VIP Excellence: All 29 pre-scheduled interviews executed flawlessly

## PILLAR 2: THEMATIC FOUNDATION

### 💡 Campaign Theme

"Impact is Powered by Innovation"
 Tagline: "Modern Tools. Timeless Truth. Maximum Reach."

This theme addresses the tension between innovation and tradition while affirming both Gospel integrity and evolving methodology.

Strategic Positioning:

- Position PRAY as the innovation partner enabling ministries to meet modern audiences where they are

- Emphasize that traditional methods alone won't reach new generations - technology is essential for mission fulfillment

- Data-driven ministry isn't a replacement for faith, it's a tool to maximize Kingdom impact

- Modern storytelling demands modern tools: mobile-first, AI-assisted, globally accessible

How This Answers "Loved, Capable, Needed":

- Loved: Ministries are valued partners in innovation, not behind-the-curve prospects

- Capable: Modern tools empower them to maximize their calling

- Needed: Their embrace of innovation is essential for reaching new generations

### 🎨 Visual Identity

Color Palette (PRAY.COM Brand)

| Color | Hex | Usage | % of Design |
| --- | --- | --- | --- |
| Black | #0B0C0D | Authority, sophistication, primary text | 45% |
| Gold | #E3AF4A | Divine inspiration, premium value, accents | 15% |
| White | #FFFFFF | Clarity, breathing room, emotional warmth | 40% |

Typography:

- Primary: Satoshi Bold (headlines, hero messaging)

- Secondary: Satoshi Regular (body copy)

- Accent: Satoshi Medium (subheadings)

Key Visual Metaphors:

- The Embrace: "Loved" - open arms, welcoming community

- The Toolbox: "Capable" - AI as empowerment tool

- The Movement: "Needed" - America Prays 250 historic moment

- The Convergence: Four 2026 initiatives uniting

### 🎭 Emotional Positioning

How Attendees Should FEEL:

- Inspired: Witnessing how innovation amplifies their calling

- Validated: Their instinct to embrace modern tools is confirmed by proven results

- Empowered: Equipped with AI and data that multiply their impact

- Confident: PRAY.COM has proven results, scientific validation, White House partnership

- Urgent: Traditional methods alone won't reach new generations - the time to innovate is now

What Attendees Should SAY:

- "They showed me how technology can amplify my ministry without compromising my message"

- "I finally understand how data-driven ministry serves Kingdom impact"

- "PRAY.COM proves that innovation and timeless truth aren't in conflict"

- "They get that we need modern tools to reach modern audiences"

- "This is what the future of evangelism looks like"

### 📝 Core Messaging Framework

Opening Statement: "Embracing technology and data can grow your mission and ministry. Storytelling is not what it was 20 years ago. Evangelism needs to advance with the times."

Three-Beat Narrative:

- THE CHALLENGE: "Traditional methods alone won't reach new generations. Modern audiences require modern tools - mobile-first, AI-assisted, globally accessible."

- THE SOLUTION: "Data-driven ministry isn't a replacement for faith, it's a tool to maximize Kingdom impact. PRAY provides the innovation that amplifies your calling."

- THE PROOF: "4.06x ROI. $6.5M pipeline from $450K investment. 557 booth guests. 97 meetings. 35 opportunities. This is what happens when impact is powered by innovation."

Power Phrases (Repeat Throughout Event):

- "Modern tools. Timeless truth. Maximum reach."

- "Innovation that amplifies your calling"

- "Data-driven. Spirit-led. Kingdom-focused."

- "Your message. Their world. Real impact."

- "Tomorrow's ministry tools. Today's results."

Featured Content Themes:

- AI-Assisted Content Creation: "Create more, faster, without sacrificing quality"

- Real-Time Audience Analytics: "Know what's working before Sunday ends"

- Global Translation at Scale: "One sermon. 100+ languages. Millions reached."

- Predictive Donor Intelligence: "Engage the right people at the right time"

- America Prays 250: "Be part of the national prayer movement" (White House partnership)

## PILLAR 3: AUDIENCE ARCHITECTURE

### 👥 Primary Audience Profile

Target Roles (From 1,614 Contacts in Database):

- Primary: Senior Pastors, Executive Pastors, Ministry Founders/CEOs

- Secondary: Media Directors, Communications Directors

- Tertiary: Development Directors, Marketing Directors

Demographics:

- Age: 35-65 years old

- Organization size: $1M+ annual budget, 5-50+ staff

- Geographic: Primarily US-based, some international

- Education: Bachelor's minimum, often seminary-trained

Psychographics:

| Motivations | Pain Points | Aspirations |
| --- | --- | --- |
| Need to demonstrate ROI to boards | Traditional broadcast reach declining | Lead thriving digital ministry |
| Want to reach digital-native believers | Donor acquisition costs unsustainable | Be recognized as innovative leader |
| Excited about AI but uncertain how to implement | Lack credible impact data | Build sustainable funding models |
| Seeking proven partners, not experimental vendors | Managing 5-10 fragmented platforms | Use tech as ministry multiplication |
| Desire to be part of something larger | Fear of being left behind | Partner with values-aligned organizations |

### 🗺️ Complete Attendee Journey

#### PRE-EVENT (6 Weeks Before → Event Day)

6-Week Email Campaign:

| Week | Subject Line | Key Message | CTA |
| --- | --- | --- | --- |
| -6 | "NRB 2026: Where Ministry Leaders Discover They're Loved, Capable & Needed" | Tease 4 initiatives + America Prays 250 | Reserve meeting slot |
| -5 | "PRAY Science: Research That Proves What You've Always Known" | Scientific validation preview | Download research brief |
| -4 | "Jack Graham Made $100K in 30 Days While Acquiring Donors" | SuperFunnel case study with numbers | Calculate your ROI |
| -3 | "America Prays 250: The White House Needs You" | National spiritual renewal movement | Learn partnership options |
| -2 | "AI Storytelling Masterclass: February 20, 9:00 AM" | Speaking session details + live demos | Add to NRB schedule |
| -1 | "193 Meetings. 29 VIP Interviews. 4 Days to Transform Your Ministry." | Practical NRB gameplan + logistics | Confirm your details |

Additional Pre-Event Touchpoints:

- Landing page: pray.com/nrb2026

- Paid advertising: LinkedIn + Meta (lookalike audiences)

- AE direct outreach: LinkedIn InMail + phone calls

- Direct mail: Top 100 accounts receive premium invitation package

#### DURING EVENT (February 17-20, 2026)

Day-by-Day Experience Arc:

Monday, Feb 17 - "Discovery & Welcome"

- Badge scan → personalized greeting

- Four experience zones available

- Pre-scheduled meetings begin (target: 48 meetings)

- Flash demos every 30 minutes

- Coffee bar: "You're loved here" branded cups

Tuesday, Feb 18 - "Deep Engagement"

- Continue meetings (target: 48 meetings)

- VIP Hour (11am-12pm): Private tours for C-level leaders

- America Prays 250 Founding Partner invitations (limited to 25)

- Evening Reception (6-8pm): Invite-only networking with executives

Wednesday, Feb 19 - "Proof & Momentum"

- "Prove It" sessions: Live ROI calculators

- SuperFunnel pilot agreements signed on-site (goal: 10)

- Continue meetings (target: 48 meetings)

- Building momentum for Friday's speaking session

Friday, Feb 20 - "Transformation & Commitment"

- SPEAKING SESSION (9:00-9:45 AM): "From Parables to Prompts: Storytelling in the Age of AI" (Delta B Ballroom)

- Post-session booth surge and speaker meet & greet

- Final meeting push (target: 49 meetings = 193 total)

- "NRB 2026 Exclusive" offer expires at booth close

#### POST-EVENT (Day 1 → 90 Days)

Follow-Up Timeline:

| Timeframe | Action | Owner | Target |
| --- | --- | --- | --- |
| Day 1 | Automated thank-you email + AE personalized videos | Nay + AEs | 655 contacts + 193 videos |
| Week 1 | Resource package email + phone calls + America Prays invite | Nay + AEs | 193 calls completed |
| Week 2 | Demo invitation + LinkedIn connections + social proof email | Nay + AEs | 77 demos scheduled (40%) |
| Week 4 | Check-in calls + custom proposals sent | AEs | 66 deals advancing |
| Day 90 | ROI calculation + re-engagement campaign + survey | Nay | 19 deals won, $2.28M revenue |
| Ongoing | Monthly newsletter + quarterly check-ins + event invitations | Marketing | Relationship maintenance |

## PILLAR 4: EXPERIENCE DESIGN

### 📍 Booth Location & Layout

Location: Delta Lobby A & B (Booth DL-B)
 View Floor Map

Booth Design Strategy:

- Maintain from 2025: Double-deck architecture, gold/black color scheme, LED lighting, VIP meeting zones

- Evolve for 2026: Innovation-focused messaging, Tier 1/2/3 leader rotation, data visualization screens

- Add for 2026: Interactive tech demonstrations (AI content creation, real-time analytics dashboards)

Strategic Design Philosophy (Based on 2025 Success):

- Prioritize intimate, data-rich consultation environments

- Double-deck VIP areas enabled 33% contact-to-meeting rate and 77% meeting-to-deal rate

- Expand premium spaces and integrate live demonstration capabilities

- Design facilitates rapid qualification (448 valid contacts in 2025)

Banner Placements (4 Total):

| Banner Type | Size | Location | Content Strategy |
| --- | --- | --- | --- |
| Hero Banner | 20'W x 30'H | Main atrium | Primary message + Tier 1 MUST leaders |
| Banner #1 | 10'W x 12'H | Overhead hall | MUST leaders: Marilyn Hickey, Jeff Schreve + Tier 1 |
| Banner #2 | 10'W x 12'H | Overhead hall | Tier 1 mix: Jentezen Franklin, Jim Daly, others |
| Banner #3 | 10'W x 12'H | Overhead hall | America Prays 250 + Tier 2/3 leaders |

Booth Interior Elements:

- Large floor-to-ceiling panels: MUST leaders (6 total) - Barry Meguiar, Jack Graham, Hank & Brenda Kunneman, Chip Ingram, Marilyn Hickey, Jeff Schreve

- Medium-format panels: Remaining Tier 1 leaders (6 total)

- Digital rotation screens: Tier 2 & 3 leaders with testimonials/metrics

- VIP meeting area: Data dashboards + selective Tier 1 leader innovation quotes

Featured Leader Tiers:

Tier 1 MUST (Non-Negotiable Visibility):

- Barry Meguiar

- Jack Graham

- Hank & Brenda Kunneman

- Chip Ingram

- Marilyn Hickey

- Jeff Schreve

Tier 1 Additional (High Priority):

- Tony Perkins, Christ In Prophecy, Tony Evans, Jentezen Franklin, Jim Daly, Rabbi Schneider

Tier 2 (Secondary Visibility):

- Nina & Michelle, Richard Ellis, GEB America, Abidan Shah, Ray Comfort

Tier 3 (Supporting Visibility - Digital Rotation):

- John Mark Caton, Voice of the Martyrs, Frank Turek

Four Experience Zones:

#### Zone 1: PRAY Science Research Theater

- 15-minute documentary on loop (85" display)

- Theater seating for 12

- Staff available for Q&A

- Takeaway: Research briefs

#### Zone 2: SuperFunnel ROI Lab

- Interactive ROI calculator

- Jack Graham case study walkthrough

- Live demo of donor acquisition model

- Conversion Moment: Sign pilot agreement on-site

#### Zone 3: America Prays 250 Experience

- Touch-screen map showing 1M prayer goal progress

- Video testimonials from partner ministries

- Digital pledge wall with signature display

- Takeaway: Partnership packets + photo op

#### Zone 4: AI Storytelling Lab

- Live PRAYStudio demonstrations

- On-demand content generation

- Hands-on workstations

- Preview: Speaking session content

Central Elements:

- Main Stage: Flash demos every 30 minutes (5 min each)

- Coffee Bar: Premium beverages + networking + charging stations ("Modern Tools. Timeless Truth." branded cups)

- Meeting Pods: Four private spaces for scheduled meetings

- Social Media Wall: Live PRAY user testimonials

### 🎁 Swag Strategy (Tiered Approach)

| Tier | Recipient | Items Included |
| --- | --- | --- |
| Tier 1 | All booth visitors | Black canvas tote, PRAY Science brief, branded pen, mints in gold tin |
| Tier 2 | Demo participants (15+ min) | Tier 1 + wireless charger, "Parables to Prompts" booklet, sticky notes |
| Tier 3 | Meeting attendees (193 target) | Tier 2 + leather journal, handwritten note, $50 restaurant gift card |
| Tier 4 | VIP prospects (29 interviews + high-value) | Tier 3 + custom gift, evening reception invite, executive contact |

### 🎤 Speaking Session Details

Title: "From Parables to Prompts: Storytelling in the Age of AI"
 Date/Time: Friday, February 20 | 9:00-9:45 AM
 Location: Delta B Ballroom
 Target Attendance: 300+ attendees

Session Structure (45 minutes):

- 0-5 min: Hook with live AI demo (generate children's Bible story in real-time)

- 5-15 min: The challenge of honoring timeless truth with exponential tools

- 15-30 min: Case studies of ministries using AI ethically

- 30-40 min: Live PRAYStudio demonstrations

- 40-45 min: PRAY Science research + CTA to visit booth

Post-Session:

- Speaker meet & greet at booth

- QR code for "Session Attendee Exclusive Offer"

- Fast-track demo scheduling

### 📧 Email Marketing Automation

Pre-Event Sequence: 6 emails over 6 weeks (detailed in Pillar 3)

Post-Event Sequence:

- Day 1: Thank-you + session recording + personalized video from AE

- Day 3: Resource package + personalized ROI calculation

- Day 5: Phone call from AE to schedule demo

- Day 7: America Prays 250 partnership invitation

- Day 10: Demo invitation with calendar link

- Day 14: Social proof email with FOMO trigger

- Day 28: Custom proposal for serious opportunities

- Day 90: 3-month update + re-engagement campaign

## PILLAR 5: OPERATIONAL EXCELLENCE

### 📅 Critical Path Timeline

| Milestone | Date | Status | Owner | Deliverable |
| --- | --- | --- | --- | --- |
| Sponsorship Confirmed | Nov 2025 | ✅ Complete | Jason Rosoff | $400K approved, booth secured |
| Creative Direction | Jan 2, 2026 (T-45) | ✅ Complete | Marketing | PB-34554 & PB-34553 approved Dec 18 |
| Email Campaign Launch | Jan 2, 2026 (T-45) | ⏳ Upcoming | Nay | Week -6 email deployed |
| Booth Production Begins | Jan 17, 2026 (T-30) | ⏳ Upcoming | Operations | Design approved, production started |
| HubSpot Testing | Jan 17, 2026 (T-30) | ⏳ Upcoming | Nay | Lead capture workflows tested |
| Booth Ships | Feb 3, 2026 (T-14) | ⏳ Upcoming | Operations | Shipped to Nashville venue |
| Team Arrives Nashville | Feb 10, 2026 (T-7) | ⏳ Upcoming | Operations | All team on-site |
| Booth Install Complete | Feb 14, 2026 (T-3) | ⏳ Upcoming | Operations | Booth ready, tech tested |
| EVENT DAYS | Feb 17-20, 2026 | ⏳ Upcoming | All Teams | 655 contacts, 193 meetings |
| Immediate Follow-Up | Feb 21, 2026 (T+1) | ⏳ Upcoming | Nay + AEs | 655 emails + 193 videos sent |
| Week 1 Outreach | Feb 28, 2026 (T+7) | ⏳ Upcoming | AEs | 193 calls completed |
| 30-Day Review | Mar 20, 2026 (T+30) | ⏳ Upcoming | Jason Rosoff | 66 deals created, $10.42M pipeline |
| 90-Day ROI | May 21, 2026 (T+90) | ⏳ Upcoming | Nay | 406% ROI, $2.28M revenue |

### ⚠️ Risk Management

| Risk | Mitigation | Owner |
| --- | --- | --- |
| Shipping delays | Ship two weeks prior (Feb 3), track shipments | Operations |
| Misaligned messaging | Pre-event alignment meeting with Sales & Marketing | Nay + Marketing |
| Tech demo issues | Backup offline demo assets prepared | Operations |
| Data loss in lead capture | HubSpot test import pre-event (by Jan 17) | Nay |
| Staff illness or travel disruption | Assign backup booth staff | Operations |
| Meeting bookings lag | Emergency outreach if <50% booked by T-21 | Nay + AEs |
| Low speaking session attendance | Boost promotion in Week -2 and Week -1 emails | Nay |

### 🚩 Red Flags to Watch

Pre-Event:

- Meeting bookings <50% by Jan 26 (T-21)

- PB-34554/PB-34553 not complete by Jan 2 (T-45)

- Target account engagement <30% response rate

- Booth production delayed past Feb 3 ship date

During Event:

- Meeting completion rate <90% by end of Day 2

- Speaking session attendance <200 people

- HubSpot data entry lag >4 hours

- Demo station tech failures

Post-Event:

- Day 1 follow-up completion <80%

- Week 1 call completion <70%

- Demo scheduling conversion <30%

- 30-day pipeline stagnation (<66 deals created)

## PILLAR 6: TEAM FUNCTION ACCOUNTABILITY

### 👥 RACI Matrix

| Function/Task | Nay | AEs | Marketing | Jason | Operations |
| --- | --- | --- | --- | --- | --- |
| Pre-Event Strategy | R | C | C | A | I |
| Email Campaign | R | I | C | A | I |
| One-Pager | R | C | C | A | I |
| Paid Ads | R | I | R | A | I |
| PB-34554 Positioning | C | C | R | A | I |
| PB-34553 Creative | C | I | R | A | I |
| Booth Design | C | I | R | A | R |
| HubSpot Lead Capture | R | R | I | I | C |
| 193 Meetings Execution | I | R | I | I | I |
| 29 VIP Interviews | I | R | I | A | I |
| Speaking Session | C | I | R | A | C |
| Evening Reception | C | R | R | A | R |
| Post-Event Follow-Up | R | R | C | I | I |
| 90-Day ROI Analysis | R | C | C | A | I |

Legend: R = Responsible | A = Accountable | C = Consulted | I = Informed

### 📋 Role-Specific Responsibilities

#### Nay Luchetti (Growth Operations - Timeline Owner)

Pre-Event:

- Build and deploy 6-week email campaign

- Create landing page (pray.com/nrb2026) with meeting request form

- Finalize One-Pager using "Impact is Powered by Innovation" positioning

- Coordinate with Marketing on booth production workflow

- Coordinate MUST leader asset collection with AEs (due Jan 5, 2026)

- Build HubSpot workflows for lead capture

- Test HubSpot import process by T-30 (mitigates data loss risk)

- Assign 1,614 contacts to AEs

- Track meeting booking pace toward 193 target

- Finalize banner PDFs for NRB portal upload (Jan 9, 2026 HARD DEADLINE)

During Event:

- Oversee HubSpot data entry quality (spot checks)

- Monitor social media and respond

- Support demo stations as needed

- Capture content for post-event use

- Nightly lead review and data cleanup

Post-Event:

- Execute automated email sequences

- Track demo scheduling conversion (target: 40%)

- Build custom proposals for opportunities

- Monitor pipeline toward $10.42M target

- Conduct 90-day ROI analysis

#### Account Executives (Matt, Robby, Russ, LS, Richard)

Pre-Event:

- Outreach to assigned accounts from 1,614 contact list

- Pre-book meetings toward 193 target

- Confirm 29 VIP interviews with assigned leaders

- Attend sales training sessions

During Event:

- Execute assigned meetings (distributed to hit 193 total)

- Deliver VIP interviews (29 pre-scheduled leaders)

- Staff demo stations during non-meeting hours

- Log all interactions in HubSpot within 2 hours

Post-Event:

- Film personalized videos to meeting attendees (Day 1)

- Call all meeting contacts within Week 1

- Move opportunities through pipeline toward 66 deals created

- Target: 19 deals won by 90 days

#### Marketing Team

Pre-Event:

- Complete PB-34554: Positioning theme (by T-45)

- Complete PB-34553: Creative direction (by T-45)

- Design booth graphics and approve production

- Create speaking session content

- Develop paid ads creative (Meta + LinkedIn)

- Design One-Pager

During Event:

- Staff booth greeting and experience zone transitions

- Manage social media live updates

- Capture photo/video content

- Host evening reception (Tuesday, Feb 18)

Post-Event:

- Edit and publish session recording

- Create recap blog post and social media highlights

- Develop case studies from newly closed customers

- Support sales with content needs

#### Jason Rosoff (Event Owner)

Pre-Event:

- Approve all strategic decisions (positioning, creative, budget)

- Review decision gates (Creative Approval at T-45)

- Final sign-off on major deliverables

During Event:

- Lead booth daily for Executive Q&A (4pm)

- Take meetings with high-value prospects

- Support speaking session delivery

- Host evening reception

Post-Event:

- Review 30-day and 90-day reports

- Approve strategic pivots based on learnings

- Support deal closing for large opportunities

- Make decision on NRB 2027 participation

#### Operations Team

Pre-Event:

- Coordinate booth production and shipping (ship by T-14)

- Book travel/accommodations for team

- Order and track swag (four tiers)

- Secure evening reception venue

During Event:

- Manage booth logistics and tech troubleshooting

- Coordinate team meals and transportation

- Handle on-site issues

- Replenish booth materials

Post-Event:

- Booth teardown and return shipping

- Reconcile expenses vs. $400K budget

- Collect feedback for improvements

- Archive event materials

### 🚦 Decision Gates

#### Gate 1: Strategic Approval ✅ PASSED

- Date: November 2025

- Decision: Sponsorship level, budget, booth, speaking session

- Approver: Jason Rosoff

- Status: Platinum sponsorship confirmed, $400K approved, Delta Lobby A & B secured

#### Gate 2: Creative Approval ✅ APPROVED - Dec 18, 2025

- Date: January 2, 2026 (T-45) - APPROVED EARLY

- Decision: PB-34554 (positioning), PB-34553 (creative), booth design, experience zones

- Approver: Jason Rosoff (Marketing VP) - APPROVED

- Approved Theme: "Impact is Powered by Innovation" with tagline "Modern Tools. Timeless Truth. Maximum Reach."

- Approved Leaders: Tier 1 MUST leaders confirmed (Barry Meguiar, Jack Graham, Hank & Brenda Kunneman, Chip Ingram, Marilyn Hickey, Jeff Schreve)

- Criteria Met: ✅ Positioning addresses innovation/tradition tension; ✅ Booth maintains "best in show" reputation; ✅ Banner strategy approved

- Status: ✅ COMPLETE - Moving to Phase 1 Design Execution

NRB 2025 Performance Context:

- ROI: 4.06x ($6.5M pipeline from $450K investment)

- Total Performance: 557 booth guests | 97 meetings | 35 opportunities | $6.46M pipeline

- Key Learning: 85 meetings booked via personal sales outreach vs. 0 from paid ads - relationship-driven pre-event outreach significantly outperformed advertising

- Conversion Success: 33% contact-to-meeting rate, 77% meeting-to-deal rate

- Average Deal Size: $115,613 (110 whale accounts engaged)

#### Gate 3: Operational Approval ⏳ UPCOMING

- Date: January 17, 2026 (T-30)

- Decision: Team readiness, HubSpot tested, travel confirmed, booth shipped, risk mitigations executed

- Approver: Operations (logistics), Nay (systems), AEs (readiness)

- Criteria: All risk mitigations executed per plan

- Status: UPCOMING

#### Gate 4: Post-Event Review ⏳ UPCOMING

- Date: March 20, 2026 (T+30)

- Decision: Performance vs. targets, lessons learned, pipeline health assessment

- Approver: Jason Rosoff (strategic), Nay (data), AEs (pipeline)

- Criteria: Did we hit 655 contacts, 193 meetings, 66 deals, $10.42M pipeline?

- Status: UPCOMING

### ✅ Success Indicators

Immediate Success (During Event):

- ✅ Booth consistently crowded

- ✅ All 193 meetings completed

- ✅ All 29 VIP interviews executed

- ✅ Speaking session standing room only (300+)

- ✅ Social media: 100+ mentions

- ✅ Attendee sentiment matches "loved, capable, needed"

30-Day Success:

- ✅ 655 captured contacts

- ✅ 193 completed meetings

- ✅ 66 deals created

- ✅ $10.42M pipeline value

- ✅ 77+ demos scheduled (40% conversion)

- ✅ 10 SuperFunnel pilots committed

- ✅ 25 America Prays 250 partnerships

90-Day Success:

- ✅ 406% ROI ($400K → $2.28M)

- ✅ $23,573 cost per deal

- ✅ 19 deals won

- ✅ NPS >50 from NRB customers

- ✅ 5+ referrals from NRB customers

- ✅ 1+ case study published

## QUICK REFERENCE

### 🔗 Important Links

- Event Website: NRB 2026

- Booth Location: Delta Lobby A & B - DL-B

- Speaking Session: Forum - From Parables to Prompts

- Jira Plan: NRB Conference 2026 Plan | Timeline

- Drive Folder: Sign in to access Google Drive Folder

- Landing Page: pray.com/nrb2026 (to be created)

### 📞 Key Contacts

| Role | Name | Responsibility |
| --- | --- | --- |
| Event Owner | Jason Rosoff | Strategic decisions, final approvals |
| Timeline Owner | Nay Luchetti | Campaign execution, HubSpot, email marketing |
| AE Team | Matt, Robby, Russ, LS, Richard | Meeting execution, VIP interviews, pipeline |
| Marketing | TBD | Creative direction, booth design, content |
| Operations | TBD | Logistics, travel, booth production |

### 📅 Key Dates at a Glance

| Date | Milestone |
| --- | --- |
| Dec 18, 2025 | ✅ Creative direction approved (PB-34554, PB-34553) |
| Dec 15, 2025 | Phase 1: Design execution & marketing review (Jason, Jose) |
| Dec 20, 2025 | Phase 2: Content validation (Max) |
| Jan 3, 2026 | Phase 3: Executive approval (Matt) |
| Jan 5, 2026 | MUST leader assets due (6 leaders from Russ, Aaron, Max, Ryan) |
| Jan 9, 2026 | HARD DEADLINE: Banner PDFs uploaded to NRB portal |
| Jan 17, 2026 | Gate 3: Operational Approval (HubSpot tested, booth production) |
| Feb 3, 2026 | Booth ships to Nashville |
| Feb 10, 2026 | Team arrives in Nashville |
| Feb 14, 2026 | Booth installation complete |
| Feb 17-20, 2026 | NRB 2026 EVENT DAYS |
| Feb 20, 9:00 AM | Speaking session: "From Parables to Prompts" |
| Feb 21, 2026 | Day 1 follow-up: 655 emails + 193 videos |
| Mar 20, 2026 | 30-day review: 66 deals, $10.42M pipeline check |
| May 21, 2026 | 90-day ROI: 406% target, $2.28M revenue |

### 🎯 Campaign Tagline

"Impact is Powered by Innovation"
 "Modern Tools. Timeless Truth. Maximum Reach."

### 📊 At-a-Glance Targets

- 655 contacts captured

- 193 meetings conducted (+27% vs 2025)

- 66 deals created (+21% vs 2025)

- $10.42M pipeline value (+21% vs 2025)

- 19 deals won (+21% vs 2025)

- $2.28M revenue target

- 406% ROI target

## 🚀 IMMEDIATE ACTION ITEMS (This Week)

### For Nay:

- ✅ COMPLETE: Creative direction approved (PB-34554 & PB-34553) - Dec 18, 2025

- 🔄 IN PROGRESS: Build email automation sequences in HubSpot (6-week campaign)

- 🔄 IN PROGRESS: Create landing page at pray.com/nrb2026

- 🔄 IN PROGRESS: Finalize One-Pager with "Impact is Powered by Innovation" positioning

- 🔄 IN PROGRESS: Build HubSpot lead capture workflows

- ⏳ NEW: Coordinate with Russ, Aaron, Max, Ryan to collect MUST leader assets by Jan 5, 2026

### For AEs (Russ, Aaron, Max, Ryan):

- ⏳ URGENT: Deliver MUST leader assets (6 leaders: Barry Meguiar, Jack Graham, Hank & Brenda K, Chip Ingram, Marilyn Hickey, Jeff Schreve) - DUE Jan 5, 2026

  - Professional headshots (300dpi minimum)

  - Action/ministry shots

  - One-sentence innovation quotes

  - Ministry logos (vector preferred)

- Begin LinkedIn outreach to assigned accounts from 1,614 list

- Confirm 29 VIP interview appointments

- Review 2026 strategic initiatives

### For Marketing (Jason, Jose):

- ✅ COMPLETE: PB-34554 and PB-34553 approved - Dec 18, 2025

- 🔄 IN PROGRESS: Phase 1 Design Execution - Banner mockups for all 4 placements - DUE Dec 15, 2025

- 🔄 IN PROGRESS: Booth graphics concepts using approved theme

- ⏳ UPCOMING: Speaking session content outline

- ⏳ UPCOMING: Develop paid ads creative (optional based on 2025 learning)

### For Jason (Marketing VP):

- ✅ COMPLETE: Approved creative direction - Dec 18, 2025

- ⏳ UPCOMING: Phase 1 Design Review - Dec 15, 2025

- Commit to Executive Q&A availability (4pm daily at booth)

### For Max (Content):

- ⏳ UPCOMING: Phase 2 Content Validation - DUE Dec 20, 2025

- Review leader imagery quality and messaging accuracy

### For Matt (Leadership):

- ⏳ UPCOMING: Phase 3 Executive Approval - DUE Jan 3, 2026

- Final sign-off on complete booth design package

## ❓ OPEN QUESTIONS

- ✅ RESOLVED: PB-34554 Positioning - "Impact is Powered by Innovation" with tagline "Modern Tools. Timeless Truth. Maximum Reach." approved Dec 18, 2025

- Email Campaign Ownership: Confirmed - Nay building email automations

- Paid Ads Budget: Recommend deprioritize based on 2025 learning (0 meetings from paid ads vs. 85 from personal outreach)

- MUST Leader Assets: Due Jan 5, 2026 from Russ, Aaron, Max, Ryan (6 leaders)

- 29 VIP Interviews: Confirm if all leaders are pre-booked or require AE outbound

- Evening Reception: Tuesday, Feb 18 format and budget details?

- Banner Production Timeline: Confirm PDFs ready for Jan 9 NRB portal upload deadline

Document Version: 2.0 (Updated with Approved Creative Direction)
 Last Updated: December 18, 2025
 Creative Approval: December 18, 2025 (Jason Rosoff, Marketing VP)
 Next Review: December 20, 2025 (Phase 2: Content Validation)
 Owner: Nay Luchetti (Timeline) | Jason Rosoff (Event)

This campaign plan uses the Six Pillars Event Strategy Framework to ensure comprehensive execution across Mission Clarity, Thematic Foundation, Audience Architecture, Experience Design, Operational Excellence, and Team Function Accountability.

Creative direction approved: "Impact is Powered by Innovation" - positioning PRAY.COM as the innovation partner that helps ministries reach modern audiences with modern tools while maintaining timeless truth.